Housing Committee Meeting Minutes:  12:30 pm May 14th, 2021 via Zoom

Attendees: Joe K., PJ, Alice, Alicia, Patrick, Irene, Al Dunn

Committee Mission:  “To support economic growth by improving the overall quality of residential and commercial properties in St. Johnsbury.”

Northern Forest Center Meeting Update RE: Workforce Housing (Joe & Irene)

Irene provided an update on the NFC workforce housing project concept.  A St. J. Workforce Housing Task Force has been organized, and a June meeting with the NFC team is forthcoming.

Housing Action Plan/Initiatives:

The group reviewed the Housing Committee Action Plan that was developed in 2018.  The Committee reviews the action plan periodically, and all agreed updates are necessary.  Joe K. will work on updating and distributing the action plan.  Patrick mentioned that strategies to address homelessness and emergency shelters is missing component from the action plan.

Patrick provided a quick update on the state’s proposed budget and the resources included for housing down-payment assistance and rental housing rehabilitation.

Patrick agreed to update the available resources addendum in the St. J. Housing Committee’s Home Buyer Incentive Program once the state budget is finalized (approx. 6 weeks).

Irene mentioned that the Committee’s Intern Program might align well with the NFC workforce housing discussion.  Joe K. agreed to reach out to Shawn Tester (NVRH) and Zach Hatch (Weidmann) to see if there is renewed interest in an intern housing program.

Patrick mentioned that the O’Dean Hale building on Main St. may be well suited for intern or workforce housing because there are no income restrictions on the building.

2021 Rental Housing Improvement Program

Joe -the application deadline was April 30th, 2021.  The Housing Review Committee is working to vet and score applications.  The Review Committee plans to make recommendations to the Select Board at the May 24th meeting.

Other Business:

- Joe - the Energy Committee is interested in downtown development discussions.  Joe suggests inviting the Energy Committee to the June or July Housing Committee meeting – All agreed.

- Landlord Newsletter- RJC continues to include rental housing information in their monthly newsletter.  Committee members are asked to provide content.

- Al Dunn asked about a housing price list for our community. Joe mentioned that he maintained an available real estate flyer quarterly, but that data did not provide rental housing rates.

Meeting adjourned at 1:45pm.  Minutes submitted by JK.

The next meeting is scheduled for June 11th, 2021, at 12:30 pm via Zoom