## Sheet1
ST. JOHNSBURY ARMORY - PROJECT TIMELINE | [21 empty] | Bidding Construction
2022-04-01 | [21 empty] | Remediation Start
|  | 2020 |  | 2021 | [7 empty] | Bond Vote |  |  |  | 2022 |  |  |  | Bidding Remediation |  |  |  |  | Construction Start |  |  | 2023 | [5 empty] | Open | [5 empty] | 2024
| Months | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Due Diligence, Design, Permitting
Assemble Project Team | 2
Civil Engineer, Geo-Tech, Structural, Architect, Environmental, Historic, LA |  | xxx | xxx
Due Diligence/Design Period: | 5
Civil Engineering/Survey/Utilities/Stormwater |  |  |  | xxx | xxx | xxx | xxx | xxx
Geo-Tech |  |  |  | xxx | xxx | xxx | xxx | xxx
Permiting Feasibility |  |  |  | xxx | xxx | xxx | xxx | xxx
Legal/Title Review |  |  |  | xxx | xxx | xxx | xxx | xxx
Architectural - programming/conceptual design/bldg elevations |  |  |  | xxx | xxx | xxx | xxx | xxx
Prepare detailed site plans for permit submittal |  |  |  | xxx | xxx | xxx | xxx | xxx
Preliminary cost estimating (for bond vote) | [9 empty] | xxx | xxx
Historic/Archeologic: | 5
Retain consultants | [6 empty] | xxx
Historic/Archeologic review; prepare Section 106 letter | [6 empty] | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
Section 106 letter review/approval by SHPO/EPA/ACHP | [16 empty] | xxx | xxx | xxx
Generate mitigation package for inclusion in MOA | [15 empty] | xxx | xxx
Prepare MOA, review/approval by SHPO/EPA/ACHP | [17 empty] | xxx | xxx | [7 empty] | Const. Start
Environmental:
EPA Targeted Brownsfield Assessment (Nobis) |  |  |  | xxx | xxx | xxx | xxx
Phase I Assessment | [15 empty] | xxx | xxx | xxx | xxx | xxx
Retain QEP to prepare ABCA, abatement plan/CAP, etc. | [13 empty] | xxx | xxx
Finalize ABCA/EPA review/public comment period | [17 empty] | xxx | xxx | xxx
Prepare RBM abatement plan/CAP, EPA review & approval | [17 empty] | xxx | xxx | xxx
Phase II work plan/soil sampling | [17 empty] | xxx | xxx
Prepare Site Specific QAPP; EPA & VDOH review & approval | [19 empty] | xxx | xxx
Cleanup Closure Report | [24 empty] | xxx | xxx
Local Permitting | 3 | [5 empty] | xxx | xxx | xxx
State Permitting:
Act 250 (Act 250 permit should not be required) | N/A
ANR Permits (Stormwater, Water/Wastewater, etc.) | 5 | [7 empty] | xxx | xxx | xxx | xxx | xxx
Final Architectural Design | 6 | [13 empty] | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
Abatement / Construction
Retain Construction Manager | [18 empty] | xxx
Environmental Abatement / Remediation
Prepare Bid Docs and Solicit Bids | 3 | [17 empty] | xxx | xxx | xxx | xxx
Execute Contract w/Abatement Contractor | [21 empty] | xxx
Commence Remediation / Remediation Completion | 6 | [20 empty] | xxx | xxx | xxx
Building/Site Construction
Prepare Bid Docs and Solicit Bids | 3 | [19 empty] | xxx | xxx | xxx
Execute Contract w/ Contractor | 1 | [21 empty] | xxx
Commence Construction / Construction Completion | 10 | [23 empty] | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
Occupy Building | 1 | [32 empty] | xxx
Financing
EPA Clean-up Grant | 500000
Submit Application |  | xxx
Award Made | [7 empty] | xxx
Money Available | [12 empty] | xxx
EPA Grant Community Outreach | [14 empty] | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
EPA Grant NHPA Requirements | [17 empty] | xxx
CDBG Slums & Blight | 500000
Begin pre-aplication
Submit Application | [18 empty] | xxx
Award Made | [20 empty] | xxx
Environmental Review
Environmental Release
Money Available
General Obligation Bond
Voter approval | [11 empty] | xxx
Money Available | TBD | [11 empty] | xxx
ACCD Brownfields Revitalization Fund | 800000
Submit Application | [18 empty] | xxx
Award Made | [19 empty] | xxx
Money Available | [20 empty] | xxx
USDA RD Community Facilities Grant | TBD
Begin pre-aplication | [25 empty] | xxx
Submit Application | 150000 | [25 empty] | xxx
Award Made | or 50,000 | [28 empty] | xxx
Money Available | [32 empty] | xxx
BGS Human Services Facilities Grant | 25000 | TBD, can't obtain grant in same year as VDHP grant
Begin pre-aplication
Submit Application (permits in hand before submitting app)
Award Made
Money Available
VT Historic Preservation Grant (Can't use in same fiscal year as BGS grant) | 20000
Begin pre-aplication | [22 empty] | xxx
Submit Application | [24 empty] | xxx
Award Made | [26 empty] | xxx
Money Available | [27 empty] | xxx
Northern Borders RC Grant (Cleanup/General Construction) | 1000000
TBD if there is an opportunity for this grant
USEDA Grant | TBD
Energy Efficiency Rebates (General Construction) | TBD
EPA Bipartisan Infrastructure Law Grant | TBD | Up to $5 M per grant available for clean up